## Title
LETS BEGIN!
Decision Precision

## car page
A
B
E
C
Q
L
D
F
T
N
M
I
H
G
J
V
P
S
O
K
U
R
Our Model

## spreadsheet
| IP | [5 empty] | IF | [9 empty] | Cost
Task | IP1 | EF (IP1) | IP2 | EF (IP2) | IP3 | EF (IP3) | IF1 | LF (IF1) | TIME (IF1) | IF2 | LF (IF2) | TIME (IF2) | IF3 | LF (IF3) | TIME (IF3) | TIME (days)
A |  | 0 |  | 0 |  | 0 | B | 32 | 30 | C | 27 | 10 | D | 21 | 7 | 2 | 200
B | A | 2 |  | 0 |  | 0 | T | 42 | 10 |  | 1000 | 0 |  | 1000 | 0 | 30 | 500
C | A | 2 |  | 0 |  | 0 | Q | 28 | 1 |  | 1000 | 0 |  | 1000 | 0 | 10 | 260
D | A | 2 |  | 0 |  | 0 | L | 22 | 1 |  | 1000 | 0 |  | 1000 | 0 | 7 | 360
E |  | 0 |  | 0 |  | 0 | F | 16 | 1 | M | 41 | 3 |  | 1000 | 0 | 1 | 100
F | E | 1 |  | 0 |  | 0 | G | 27 | 4 | H | 22 | 6 | I | 17 | 1 | 1 | 300
G | F | 2 |  | 0 |  | 0 | R | 28 | 1 |  | 1000 | 0 |  | 1000 | 0 | 4 | 400
H | F | 2 |  | 0 |  | 0 | O | 23 | 1 |  | 1000 | 0 |  | 1000 | 0 | 6 | 600
I | F | 2 |  | 0 |  | 0 | J | 22 | 3 | K | 22 | 5 | L | 22 | 1 | 1 | 100
J | I | 3 |  | 0 |  | 0 | O | 23 | 1 |  | 1000 | 0 |  | 1000 | 0 | 3 | 600
K | I | 3 |  | 0 |  | 0 | N | 23 | 1 |  | 1000 | 0 |  | 1000 | 0 | 5 | 1000
L | D | 9 | I | 3 |  | 0 | N | 23 | 1 |  | 1000 | 0 |  | 1000 | 0 | 1 | 100
M | E | 1 |  | 0 |  | 0 | U | 42 | 1 |  | 1000 | 0 |  | 1000 | 0 | 3 | 300
N | K | 8 | L | 10 |  | 0 | P | 27 | 4 |  | 1000 | 0 |  | 1000 | 0 | 1 | 300
O | H | 8 | J | 6 |  | 0 | P | 27 | 4 |  | 1000 | 0 |  | 1000 | 0 | 1 | 160
P | N | 11 | O | 9 |  | 0 | R | 28 | 1 |  | 1000 | 0 |  | 1000 | 0 | 4 | 1400
Q | C | 12 |  | 0 |  | 0 | S | 32 | 4 |  | 1000 | 0 |  | 1000 | 0 | 1 | 140
R | G | 6 | P | 15 |  | 0 | S | 32 | 4 |  | 1000 | 0 |  | 1000 | 0 | 1 | 120
S | Q | 13 | R | 16 |  | 0 | U | 42 | 1 | T | 42 | 10 |  | 1000 | 0 | 4 | 3400
T | B | 32 | S | 20 |  | 0 | V | 44 | 2 |  | 1000 | 0 |  | 1000 | 0 | 10 | 2400
U | M | 4 | S | 20 |  | 0 | V | 44 | 2 |  | 1000 | 0 |  | 1000 | 0 | 1 | 100
V | T | 42 | U | 21 |  | 0 |  | 1000 | 0 |  | 1000 | 0 |  | 1000 | 0 | 2 | 1000
[9 empty] | 0 |  |  | 0 |  |  | * Total Time | 99
|  | EF | LF |  | ES | LS |  | Slack | Critical Path | Longest Path | [5 empty] | Total Cost | 13840
|  | 2 | 2 |  | 0 | 0 |  | 0 | A | 2
|  | 32 | 32 |  | 2 | 2 |  | 0 | B | 30
|  | 12 | 27 |  | 2 | 17 |  | 15
|  | 9 | 21 |  | 2 | 14 |  | 12
|  | 1 | 15 |  | 0 | 14 |  | 14
|  | 2 | 16 |  | 1 | 15 |  | 14
|  | 6 | 27 |  | 2 | 23 |  | 21 | [6 empty] | * Total Time will equal the Completion Time if the tasks can not be done simultaneously.
|  | 8 | 22 |  | 2 | 16 |  | 14
|  | 3 | 17 |  | 2 | 16 |  | 14
|  | 6 | 22 |  | 3 | 19 |  | 16
|  | 8 | 22 |  | 3 | 17 |  | 14
|  | 10 | 22 |  | 9 | 21 |  | 12
|  | 4 | 41 |  | 1 | 38 |  | 37
|  | 11 | 23 |  | 10 | 22 |  | 12
|  | 9 | 23 |  | 8 | 22 |  | 14
|  | 15 | 27 |  | 11 | 23 |  | 12
|  | 13 | 28 |  | 12 | 27 |  | 15
|  | 16 | 28 |  | 15 | 27 |  | 12
|  | 20 | 32 |  | 16 | 28 |  | 12
|  | 42 | 42 |  | 32 | 32 |  | 0 | T | 10
|  | 21 | 42 |  | 20 | 41 |  | 21
|  | 44 | 44 |  | 42 | 42 |  | 0 | V | 2
[8 empty] | Completion Time |  | 44
Gantt Chart

## gantt chart
Task | Time
A | 2
B | 30
C | 10
D | 7
E | 1
F | 1
G | 4
H | 6
I | 1
J | 3
K | 5
L | 1
M | 3
N | 1
O | 1
P | 4
Q | 1
R | 1
S | 4
T | 10
U | 1
V | 2
Cost Chart

## cost chart
Task | Cost
A | 200
B | 500
C | 260
D | 360
E | 100
F | 300
G | 400
H | 600
I | 100
J | 600
K | 1000
L | 100
M | 300
N | 300
O | 160
P | 1400
Q | 140
R | 120
S | 3400
T | 2400
U | 100
V | 1000
total | 13840
1160
Credits
Back to the Beginning

## credits
Team Members | Position Held
Pamela Ortiz | Leader
Danielle DiGeorgio | Project Supervisor
Nick Barbato | Ecourager
Chantal Sparkes | Secretary
Credits
Back to the Beginning